## Data
Status | Priority | Severity | Module
Not Run | High | Critical | Login
Passed | Medium | High | Logout
Failed | Low | Medium | Session
Blocked |  | Low | Catalog
N/A |  | Trivial | Search
Filters
Sorting
Product Details
Cart
Checkout
Validation
Responsive
Browser Behavior
Accessibility
Security
API

## Test Plan
Section | Content
Project Name | Manual Testing of a Web Marketplace Application
Application Under Test | https://practicesoftwaretesting.com/
Application Type | Demo marketplace / e-commerce web application
Tester | Bohdan Mamedov
Test Period | 2026-07-02 – 2026-07-07
Project Overview | This project focuses on manual testing of a marketplace-style web application. The goal is to verify key user flows, identify functional issues, and create clear QA documentation.
Scope of Testing | Product catalog, search, filters, sorting, product details page, cart, checkout flow, login, registration, validation messages, browser back button behavior, responsive layout, basic accessibility checks, basic security checks.
Out of Scope | Real payment transactions, performance testing, security penetration testing, backend/database testing, and automation testing.
Testing Types | Manual functional testing, UI testing, regression testing, responsive testing, basic accessibility testing, basic security testing.
Test Environment | OS: Windows 11; Browsers: Google Chrome
Entry Criteria | Application is accessible; main user flows are available; test data is prepared; browser/device setup is ready.
Exit Criteria | Main test cases are executed; critical/major defects are documented; regression checklist is completed; test summary report is prepared.
Risks | Some functionality may be limited on demo websites; real payment testing may not be possible; some defects may be environment-specific.
Deliverables | Test Plan, Functional Checklist, Test Cases, Bug Reports, Regression Checklist, Test Summary Report.

## Checklist
ID | Module | Check | Priority | Status | Environment | Notes
CH-001 | Login | Verify that login page opens correctly | High | Passed | Windows 11 / Chrome
CH-002 | Login | Verify login with valid credentials | High | Passed | Windows 11 / Chrome
CH-003 | Login | Verify error message for empty email/username field | High | Passed | Windows 11 / Chrome
CH-004 | Login | Verify error message for empty password field | High | Passed | Windows 11 / Chrome
CH-005 | Login | Verify error message for wrong password | High | Passed | Windows 11 / Chrome
CH-006 | Login | Verify that password is hidden by default | Medium | Passed | Windows 11 / Chrome
CH-007 | Login | Verify case sensitivity for username/email when applicable | Medium | Passed | Windows 11 / Chrome
CH-008 | Login | Verify special characters in username/password fields | Medium | Passed | Windows 11 / Chrome
CH-009 | Logout | Verify that user can log out successfully | High | Passed | Windows 11 / Chrome
CH-010 | Session | Verify that user cannot access account/cart pages after logout using browser Back button | High | Passed | Windows 11 / Chrome
CH-011 | Session | Verify that page refresh keeps user logged in when session is active | Medium | Passed | Windows 11 / Chrome
CH-012 | Catalog | Verify that product/resource catalog opens correctly | High | Passed | Windows 11 / Chrome
CH-013 | Catalog | Verify that product/resource cards display title, image, and price/status | High | Passed | Windows 11 / Chrome
CH-014 | Catalog | Verify that product/resource list does not show broken images | Medium | Passed | Windows 11 / Chrome
CH-015 | Catalog | Verify that catalog pagination or infinite scroll works if available | Medium | Passed | Windows 11 / Chrome
CH-016 | Search | Verify that search returns relevant results for valid keyword | High | Passed | Windows 11 / Chrome
CH-017 | Search | Verify search with no matching results | Medium | Passed | Windows 11 / Chrome
CH-018 | Search | Verify search with special characters | Medium | Passed | Windows 11 / Chrome
CH-019 | Search | Verify search field trimming for leading/trailing spaces | Medium | Passed | Windows 11 / Chrome
CH-020 | Search | Verify search result count/message if available | Low | Passed | Windows 11 / Chrome
CH-021 | Filters | Verify applying one filter updates results correctly | High | Passed | Windows 11 / Chrome
CH-022 | Filters | Verify applying multiple filters updates results correctly | High | Passed | Windows 11 / Chrome
CH-023 | Filters | Verify removing filters restores broader results | High | Passed | Windows 11 / Chrome
CH-024 | Filters | Verify filter state after page refresh if applicable | Medium | Failed | Windows 11 / Chrome | After refreshing the page, selected checkboxes and filter settings are reset instead of being preserved.
CH-025 | Filters | Verify no-results state after restrictive filters | Medium | Passed | Windows 11 / Chrome
CH-026 | Sorting | Verify sorting by price/name/relevance if available | Medium | Passed | Windows 11 / Chrome
CH-027 | Sorting | Verify sorting remains consistent after pagination or page reload | Medium | Failed | Windows 11 / Chrome | Selected sorting option is not preserved after page refresh. After reloading the page, the product list returns to the default sorting order.
CH-028 | Product Details | Verify product/resource details page opens from catalog | High | Passed | Windows 11 / Chrome
CH-029 | Product Details | Verify title, description, price, preview/image, and metadata are shown | High | Passed | Windows 11 / Chrome
CH-030 | Product Details | Verify broken/missing preview is handled correctly | Medium | Blocked | Windows 11 / Chrome | Test case could not be executed because the demo application does not provide a product with a broken or missing preview image.
CH-031 | Product Details | Verify navigation back to catalog preserves context if applicable | Medium | Failed | Windows 11 / Chrome | After navigating from a product details page back to the catalog, the previous catalog context is not preserved. Filters, sorting, and/or scroll position are reset.
CH-032 | Cart | Verify adding one item to cart | High | Passed | Windows 11 / Chrome
CH-033 | Cart | Verify cart counter updates after adding item | High | Passed | Windows 11 / Chrome
CH-034 | Cart | Verify adding the same item twice is handled correctly | Medium | Passed | Windows 11 / Chrome
CH-035 | Cart | Verify removing item from cart | High | Passed | Windows 11 / Chrome
CH-036 | Cart | Verify cart total updates after changes | High | Passed | Windows 11 / Chrome
CH-037 | Cart | Verify empty cart state | Medium | Passed | Windows 11 / Chrome
CH-038 | Cart | Verify cart persists after page refresh if expected | Medium | Passed | Windows 11 / Chrome
CH-039 | Checkout | Verify checkout page opens from cart | High | Passed | Windows 11 / Chrome
CH-040 | Checkout | Verify required field validation on checkout form | High | Passed | Windows 11 / Chrome
CH-041 | Checkout | Verify valid checkout flow up to confirmation/last safe step | High | Passed | Windows 11 / Chrome
CH-042 | Checkout | Verify invalid email/phone/postal code validation if fields exist | Medium | Passed | Windows 11 / Chrome | Fields accept test data, but basic format validation is applied. Phone field requires numeric input, and email/postal code fields require valid formats where applicable.
CH-043 | Checkout | Verify checkout cannot be completed with empty cart | High | Passed | Windows 11 / Chrome
CH-044 | Validation | Verify clear and user-friendly validation messages | High | Failed | Windows 11 / Chrome | Validation messages are generally clear and user-friendly when displayed. Field length and format validation messages clearly explain the issue. Missing required-field messages in the checkout billing address form are tracked separately in CH-060 / BR-004.
CH-045 | Validation | Verify validation messages disappear after correcting input | Medium | Passed | Windows 11 / Chrome
CH-046 | Validation | Verify long text input does not break layout | Medium | Passed | Windows 11 / Chrome
CH-047 | Browser Behavior | Verify browser Back button behavior after login | Medium | Passed | Windows 11 / Chrome
CH-048 | Browser Behavior | Verify browser Back button behavior from checkout to cart | Medium | Passed | Windows 11 / Chrome
CH-049 | Browser Behavior | Verify page refresh does not duplicate cart/order action | High | Passed | Windows 11 / Chrome
CH-050 | Browser Behavior | Verify opening product details in new tab if supported | Low | Passed | Windows 11 / Chrome
CH-051 | Responsive | Verify layout on mobile viewport 360x800 | High | Passed | Windows 11 / Chrome
CH-052 | Responsive | Verify layout on tablet viewport 768x1024 | Medium | Passed | Windows 11 / Chrome
CH-053 | Responsive | Verify navigation menu on mobile | High | Passed | Windows 11 / Chrome
CH-054 | Responsive | Verify forms are usable on mobile | High | Passed | Windows 11 / Chrome
CH-055 | Responsive | Verify no horizontal scrolling on mobile unless expected | Medium | Passed | Windows 11 / Chrome
CH-056 | Responsive | Verify buttons are large enough to tap on mobile | Medium | Passed | Windows 11 / Chrome
CH-057 | Accessibility | Verify input fields have visible labels or placeholders | Medium | Passed | Windows 11 / Chrome
CH-058 | Accessibility | Verify main buttons have clear readable text | Medium | Passed | Windows 11 / Chrome
CH-059 | Accessibility | Verify keyboard Tab navigation through main form fields | Medium | Passed | Windows 11 / Chrome
CH-060 | Accessibility | Verify error messages are visible and understandable | Medium | Failed | Windows 11 / Chrome | Required billing address fields do not show validation messages when empty. The "Proceed to checkout" button remains disabled, but the user is not clearly informed which fields must be completed.
CH-061 | Security | Verify password is not visible in URL or page text | High | Passed | Windows 11 / Chrome
CH-062 | Security | Verify restricted pages require authentication | High | Passed | Windows 11 / Chrome
CH-063 | Security | Verify user cannot complete restricted action after logout | High | Passed | Windows 11 / Chrome
CH-064 | Security | Verify basic XSS-like input does not execute in text fields | Medium | Passed | Windows 11 / Chrome
CH-065 | General UI | Verify no obvious spelling mistakes in main user flows | Low | Passed | Windows 11 / Chrome
CH-066 | General UI | Verify important buttons have consistent labels | Low | Passed | Windows 11 / Chrome
CH-067 | Accessibility | Verify keyboard navigation through user account dropdown | Medium | Failed | Windows 11 / Chrome | User account dropdown is partially accessible by keyboard, but the "Sign out" option cannot be reached using Tab. Pressing Tab closes the dropdown menu instead.

## Test Cases
Test Case ID | Module | Title | Preconditions | Test Data | Steps | Expected Result | Actual Result | Priority | Status | Bug ID / Notes
TC-001 | Login | Login with valid credentials | User has a valid active account | Valid email/password | 1. Open login page 2. Enter valid email 3. Enter valid password 4. Click Login | User is logged in successfully and redirected to the account page | User is logged in successfully and redirected to the account page. | High | Passed
TC-002 | Login | Login with empty password | Login page is open | Valid email/empty password | 1. Enter valid email 2. Leave password field empty 3. Click Login | A clear validation message is displayed and user is not logged in | Validation message is displayed for the empty password field and user is not logged in. | High | Passed
TC-003 | Login | Login with wrong password | Login page is open | Valid email, invalid password | 1. Enter valid email 2. Enter wrong password 3. Click Login | Error message is displayed and user remains on login page | Error message is displayed and user remains on the login page. | High | Passed
TC-004 | Session | Access restricted page after logout | User is logged in and has opened a restricted page | N/A | 1. Log out 2. Click browser Back button 3. Refresh page if needed | Restricted content is not accessible after logout | Restricted content is not accessible after logout. User is redirected to login page | High | Passed
TC-005 | Catalog | Open catalog page | Application is accessible | N/A | 1. Open catalog page | Catalog page loads and product cards are visible | Catalog page loads successfully and product cards are visible | High | Passed
TC-006 | Search | Search by valid keyword | Catalog page is open | Keyword that should return results | 1. Enter valid keyword in search field 2. Submit search | Relevant search results are displayed | Relevant search results are displayed for the entered keyword. | High | Passed
TC-007 | Search | Search with no matching results | Catalog page is open | Random unlikely keyword | 1. Enter unlikely keyword 2. Submit search | No-results state is displayed clearly | No-results state is displayed clearly for a keyword with no matching products | Medium | Passed
TC-008 | Filters | Apply category/subject filter | Catalog page is open | Available filter value | 1. Select a filter 2. Observe result list | Only relevant filtered results are displayed | Only products matching the selected filter are displayed. | High | Passed
TC-009 | Filters | Clear selected filter | A filter is applied | Selected filter | 1. Click Clear filter | Filter is removed and results are updated | Selected filter is removed and product results are updated. | High | Passed
TC-010 | Sorting | Sort catalog results | Catalog page is open | Available sorting option | 1. Open sorting dropdown 2. Select sorting option | Results are reordered according to selected sorting option | Product list is reordered according to the selected sorting option. | Medium | Passed
TC-011 | Product Details | Open product details page | Catalog page has at least one item | Any visible item | 1. Click an item card | Details page opens and displays correct item information | Product details page opens and displays product name, image, price, description, and Add to cart button. | High | Passed
TC-012 | Cart | Add item to cart | User can access catalog/product page | Any available item | 1. Open item page 2. Click Add to cart | Item is added to cart and cart counter/summary updates | Item is added to cart and cart quantity is updated. | High | Passed
TC-013 | Cart | Remove item from cart | Cart contains one item | N/A | 1. Open cart 2. Click Remove for item | Item is removed and cart total updates | Item is removed from cart and cart total is updated. | High | Passed
TC-014 | Cart | Empty cart state | Cart is empty | N/A | 1. Open cart with no items | Clear empty cart message is displayed | Empty cart message is displayed clearly. | Medium | Passed
TC-015 | Checkout | Proceed to checkout with item in cart | Cart contains at least one item | N/A | 1. Open cart 2. Click Checkout | Checkout page opens successfully | Checkout page opens successfully with the selected item in the cart. | High | Passed
TC-016 | Checkout | Required field validation in checkout | Checkout page is open | Empty required fields | 1. Leave required fields empty 2. Click Continue/Submit | Validation messages are shown for required fields | No validation messages are displayed for empty required billing address fields. The "Proceed to checkout" button remains disabled. | High | Failed | BR-004
TC-017 | Checkout | Complete safe checkout flow | Checkout page is open; no real payment required | Valid checkout data | 1. Fill required fields 2. Continue to final safe confirmation step | User reaches confirmation/final step without errors | User reaches the confirmation without errors using valid test checkout data. | High | Passed
TC-018 | Responsive | Verify mobile layout | Application is open in browser DevTools | Viewport 360x800 | 1. Open DevTools 2. Switch to mobile viewport 3. Check main pages | Layout is readable and usable without critical overlap or broken controls | Layout is readable and usable on 360x800 mobile viewport. No critical overlap, broken controls, or unexpected horizontal scrolling were found. | High | Passed
TC-019 | Accessibility | Keyboard navigation through login form | Login page is open | Keyboard only | 1. Press Tab through fields and buttons 2. Press Enter on Login button | Focus order is logical and form can be used with keyboard | Keyboard focus moves through login form fields and buttons in a logical order. The login form can be used with keyboard navigation. | Medium | Passed
TC-020 | Security | Basic script input in text field | A text input/search field is available | <script>alert(1)</script> | 1. Enter script-like input 2. search 3. Observe page behavior | Input is treated as text or safely rejected; no script executes | Script-like input is treated as plain text or safely rejected. No script is executed. | Medium | Passed
TC-021 | Accessibility | Keyboard navigation through user account dropdown | User is logged in | Keyboard only | 1. Navigate to the user account menu using Tab. 2. Open the account dropdown menu. 3. Press Tab to move through dropdown items. 4. Reach and activate the "Sign out" option using keyboard. | All dropdown menu items, including "Sign out", should be reachable and actionable using keyboard navigation. | "Sign out" cannot be reached using Tab navigation. Pressing Tab closes the dropdown instead of moving focus to the "Sign out" option. | Medium | Failed | BR-005
TC-022 | Filters | Filter state after page refresh | Catalog page is open | Any available filter | 1. Open catalog page 2. Select one or more filters 3. Verify that filtered results are displayed 4. Refresh the page | Selected filters remain active after page refresh | Selected filters are reset after page refresh. Checkboxes become unchecked and default catalog results are displayed. | Medium | Failed | BR-001
TC-023 | Sorting | Sorting state after page refresh | Catalog page is open | Any available sorting option | 1. Open catalog page 2. Select a sorting option 3. Verify that products are sorted 4. Refresh the page | Selected sorting option remains active and product order stays consistent | Selected sorting option is reset after page refresh and product list returns to the default sorting order. | Medium | Failed | BR-002
TC-024 | Product Details | Catalog context after returning from product details | Catalog page is open; filters/sorting or scroll position are applied | Any product | 1. Open catalog page 2. Apply filter or sorting 3. Scroll down the product list 4. Open a product details page 5. Navigate back to catalog | Previous catalog context is preserved, including filters, sorting, and/or scroll position | Previous catalog context is not preserved. User is returned to the default catalog state. | Medium | Failed | BR-003

## Bug Reports
Bug ID | Title | Severity | Priority | Environment | Preconditions | Steps to Reproduce | Actual Result | Expected Result | Related Check / Test Case | Status
BR-001 | Selected filters are reset after page refresh | Low | Medium | Windows 11 / Chrome | Product catalog page is open. | 1. Open the product catalog page. 2. Select one or more filters. 3. Verify that filtered results are displayed. 4. Refresh the page. | Selected filters are not preserved after page refresh. Checkboxes are reset and the catalog returns to the default state. | Selected filters should remain active after page refresh, and the filtered result list should be preserved. | CH-024 TC-022 | Open
BR-002 | Selected sorting option is reset after page refresh | Low | Medium | Windows 11 / Chrome | Product catalog page is open. | 1. Open the product catalog page. 2. Select any sorting option. 3. Verify that the product list is sorted. 4. Refresh the page. | Selected sorting option is not preserved after page refresh. The product list returns to the default sorting order. | Selected sorting option should remain active after page refresh, and the product order should stay consistent. | CH-027 TC-023 | Open
BR-003 | Catalog context is not preserved after returning from product details page | Low | Medium | Windows 11 / Chrome | Product catalog page is open. Filter, sorting, or scroll position is applied. | 1. Open the product catalog page. 2. Apply a filter or sorting option. 3. Scroll down the product list. 4. Open a product details page. 5. Navigate back to the catalog page. | Previous catalog context is not preserved after returning from product details. Filters, sorting, and/or scroll position are reset. | The application should preserve the previous catalog context after returning from product details, including filters, sorting, and/or scroll position where applicable. | CH-031 TC-024 | Open
BR-004 | Missing validation messages for required billing address fields | Medium | Medium | Windows 11 / Chrome | User is logged in and has at least one item in the cart. Checkout Billing Address step is open. | 1. Open the cart. 2. Proceed to checkout. 3. Go to the Billing Address step. 4. Leave required fields empty. 5. Observe the form state. | No validation messages are displayed for empty required billing address fields. The "Proceed to checkout" button remains disabled without explaining which fields must be completed. | The application should clearly indicate which required fields are missing, either by displaying validation messages near the fields or by showing clear field-level validation after user interaction. | CH-060 TC-016 | Open
BR-005 | Sign out option is not accessible via keyboard navigation | Medium | Medium | Windows 11 / Chrome | User is logged in. | 1. Navigate to the user account dropdown using keyboard Tab navigation. 2. Open the account dropdown menu. 3. Press Tab to move through the dropdown options. 4. Try to reach and activate the "Sign out" option using keyboard. | The "Sign out" option cannot be reached using Tab navigation. Pressing Tab closes the dropdown menu instead of moving focus to the "Sign out" option. | All user account dropdown options, including "Sign out", should be reachable and actionable using keyboard navigation. | CH-067 TC-021 | Open

## Regression
ID | Area | Scenario | When to Run | Priority | Status | Notes
RG-001 | Login | Valid user can log in | Before each release | High | Not Run
RG-002 | Login | Invalid login is rejected with clear error | Before each release | High | Not Run
RG-003 | Logout | User can log out | Before each release | High | Not Run
RG-004 | Session | Restricted pages are not accessible after logout | Before each release | High | Not Run
RG-005 | Catalog | Catalog/resources page loads | Before each release | High | Not Run
RG-006 | Search | Search returns relevant results | Before each release | High | Not Run
RG-007 | Filters | Main filters work correctly | Before each release | High | Not Run
RG-008 | Sorting | Sorting works correctly | Before each release | Medium | Not Run
RG-009 | Product Details | Details page opens and displays item data | Before each release | High | Not Run
RG-010 | Cart | Item can be added to cart | Before each release | High | Not Run
RG-011 | Cart | Item can be removed from cart | Before each release | High | Not Run
RG-012 | Cart | Cart total/counter updates correctly | Before each release | High | Not Run
RG-013 | Checkout | Checkout page opens from cart | Before each release | High | Not Run
RG-014 | Checkout | Required field validation works | Before each release | High | Not Run
RG-015 | Checkout | Safe checkout flow reaches final step | Before each release | High | Not Run
RG-016 | Validation | Error messages are clear and visible | Before each release | Medium | Not Run
RG-017 | Browser | Back/refresh behavior does not break main flow | Before each release | Medium | Not Run
RG-018 | Responsive | Main flows are usable on mobile viewport | Before each release | High | Not Run
RG-019 | Accessibility | Main form can be used with keyboard | Before major release | Medium | Not Run
RG-020 | Security | Password/restricted data are not exposed | Before each release | High | Not Run

## Test Summary
Test Summary Report
Project | Manual Testing of a Web Marketplace Application
Tester | Bohdan Mamedov
Application / URL | Practice Software Testing — Toolshop https://practicesoftwaretesting.com/
Test Period | 2026-07-02 – 2026-07-07
Environment | Windows 11; Chrome; Chrome DevTools responsive view
Metric | Checklist | Test Cases | Regression | Bug Reports | Notes
Total | 67 | 24 | 20 | 5
Passed | 60 | 19 | 0
Failed | 6 | 5 | 0
Blocked | 1 | 0 | 0
Not Run | 0 | 0 | 20
Open Bugs |  |  |  | 5
Critical/High Bugs |  |  |  | 0
Regression suite was prepared but not executed, as this is a demo portfolio project.